## Slide 1: Joint Hurricane Test Bed (JHT) Progress and Future Plans
USWRP
Dr. Jiann-Gwo Jiing JHT Director Chief, TSB TPC/NHC 3 March 2004

## Slide 2: Outline
Project Assessments 2002-03
Status of 10 First Round Projects (FY01-02)
Summary of Second Round Projects Funded in Late FY03
JHT Future Plans
JHT Issues

## Slide 3
IT configuration and algorithm processing provided for each project to facilitate forecaster participation
Real-time testing and evaluation activities continued during 2003 season
PIs presented updates at 57th Interdepartmental Hurricane Conference (IHC) (Mar 2003)
FY01-02 projects concluded (Jun-Aug 2003)
JHT reports to TPC/NHC Director on results from 2002-03 hurricane seasons (Nov 2003)
TPC/NHC decisions for operational implementation (Dec 2003)
Project Assessments 2002-03

## Slide 4: Input for JHT Project Reports to the TPC Director
Project PI final report
JHT staff members’ assessments
TPC Point of Contact (POC) feedback
JHT IT Facilitator report
  IT transfer status
  Compatibility and support issues
  Estimates of costs to implement and support
  Input from TPC Technical Support Branch Chief

## Slide 5
Provide baseline TC rainfall forecasts for assessing skill of other methods
Develop R-CLIPER from gauge and TMI climatology for operational and model QPF comparisons
Project climatology along forecast track
Example: Development of a Tropical Cyclone Rainfall
Climatology and Persistence (R-CLIPER) Model
PI: Frank Marks (NOAA/AOML/HRD)
POC: Stacy Stewart and Hugh Cobb (TPC), David Roth (HPC)
Status: Accepted by TPC for operational implementation

## Slide 6
Example: Development of a Tropical Cyclone Rainfall
Climatology and Persistence (R-CLIPER) Model
Considerations for operational implementation decision
Favorable:
Provides baseline forecast, as originally intended, needed to evaluate the skill of other sources of TC rainfall guidance (primarily dynamical models, as in the new JHT project funded in FY03)
TPC and HPC forecasters have found the guidance to be useful operationally (e.g., for preparing generalized rainfall information in public advisories)
Code has been transferred to TPC where it is run and maintained locally
Gempak/NMAP2 graphical output already routinely available to specialists for each active TC in the Atlantic and eastern North Pacific basins
Negligible CPU, disk space, memory to run; minimal support required
Unfavorable:
Unclear reason for needed adjustment factor to final output
Verification results not yet completed
Does not account for storm asymmetries

## Slide 7
Example: Development of a Tropical Cyclone Rainfall
Climatology and Persistence (R-CLIPER) Model
Example real-time output in NAWIPS during Hurricane Lili (2002)

## Slide 8
Example: Development of a Tropical Cyclone Rainfall
Climatology and Persistence (R-CLIPER) Model
Example content for IT report to TPC Director

## Slide 9: Factors Considered in TPC Decisions for Operational Implementation
Forecast or Analysis Benefit: expected improvement in operational forecast and/or analysis accuracy
Efficiency: adherence to forecaster time constraints and ease of use needs
Compatibility: IT compatibility with operational hardware, software, data, communications, etc.
Sustainability: availability of resources to operate, upgrade, and/or provide support

## Slide 10
Status of 10 First Round Projects (FY01-02)
Ten projects were funded in FY01
One was denied second year funding
Six were accepted for operational
implementation
Decisions on two projects were deferred until
the completion of closely related new projects
One was not accepted for operational
implementation at this time

## Slide 11
Summary of Second Round of Projects Funded in Late FY03

## Slide 12
Open to government, academic, and private sector applicants worldwide
Estimated total available funding $1.5M
Federal Register Notice (FRN) released 3 January 2003

## Slide 13
FY03 Review Process
Preapplications (Letters of Intent) reviewed in February 2003
  34 preapplications received
  24 recommended to submit a full proposal
Full proposals reviewed during April and May 2003
  24 full proposals received
  Proposals independently reviewed and scored by 7-member review panel based upon six review criteria listed in the FRN

## Slide 14
FY03 Selection Process
Recommendations and Selections (Jun – Sep 2003)
  Proposal rank determined by the average of total scores from all (non-recused) reviewers
  TPC/JHT Directors recommended funding 16 proposals
  15 new projects funded for summer 2003 – summer 2004 (one of selected 16 withdrawn)
  3 one-year projects and 12 two-year projects (latter will be reviewed after first year for a second year of funding)

## Slide 15
Primary Area of Focus | # of Projects
Improvements to dynamical models (for track, intensity, and precipitation forecasts) | 4
Track forecast guidance algorithms | 3
Intensity forecasting algorithms | 3
Enhancements to observed data, assimilation | 2
Initial intensity estimation | 1
Tropical cyclogenesis | 1
Rainfall | 1
Total | 15
FY03 Funded Project Focus Areas

## Slide 16: TPC/NHC Project Points of Contact
Forecaster
  15 projects, 6 specialists
  3 specialists handle 3 projects each, other 3 handle 2 projects each
  Additional TAFB and/or HSM contacts where desired
  Real-time evaluation, verification, written reports
Technical
  Needed for some projects
  Assist PI, their staff, and JHT Facilitator in setup of code, data, etc. for testing and evaluation
  Provide input to JHT staff on written assessments

## Slide 17
FY03 Funding Distribution Total $1.35M (another $150K unused)

## Slide 18
Funding Distribution Comparison Increased funding to researchers outside of NOAA
FY2003 $1.35M
FY2002 $1.2M

## Slide 19
JHT Future Plans
Round Two projects (FY03-04 funding)
  Review each project for second year of funding (FY04)
  Real-time testing and evaluation during 2004 hurricane season, and part of 2005 season
  Submit results to TPC in late 2005 for decisions on operational implementation
Round Three projects (FY05-06 funding)
  Develop new announcement of opportunity for early FY05 release
  Anticipating similar areas of focus as for Round Two
  Oct 2004 – Mar 2005: review, select, and fund new set of projects
  Real-time testing and evaluation during 2005 and 2006 hurricane seasons (could be delayed for one season if funding schedule is delayed)

## Slide 20: JHT Issues
Perceptions
  Lack of initial fairness and openness
    Addressed by the JHT Federal Register Notice in 2003
  NOAA laboratories have an unfair advantage over non-NOAA research institutions
    More than half of the funds awarded in FY 03 went to non-NOAA institutions
    JHT Steering Committee comprises four non-NOAA members and three NOAA members
  Closed to innovative modeling approaches
    Will be addressed by the Developmental Test Bed (DTC)
Heavy workload for TPC
  Impact on administrative, technical, and operations staff
    TPC and JHT staffs are identifying ways to streamline and delegate work, based on lessons learned from completion of a full first round of projects

## Slide 21: JHT Issues continued
IT compatibility
  Potential lack of resources for operational implementation of beneficial, cutting-edge techniques
    Will seek funding to implement such techniques as needs arise
Funding cycle and schedule
  Lengthy process from announcement of opportunity to dispersal of funds to non-NOAA participants
    NOAA is addressing the grants applications and awards process
  Asynchronous with hurricane season (would be highly desirable for projects to not miss a hurricane season)
    USWRP and JHT staffs working together on viable options, including earlier release of announcement of opportunity

## Slide 22
Thank you

## Slide 23: FY03 Point of Contact Distribution Dynamical model upgrades, obs/assimilation projects
Proposal | PIs | TPC POC | Yrs
Upgrades to the operational GFDL hurricane prediction system | Bender | Pasch Rhome | 2
Improving the GFDL/URI coupled hurricane-ocean model | Ginis | Pasch Rhome | 2
Hurricane model transitions to operations at NCEP/EMC | Pan | Pasch Rhome | 2
Evaluation of upper ocean mixing parameterizations | Jacob Shay Halliwell | Lawrence Mainelli | 2
Real-time dissemination of hurricane wind fields determined from airborne doppler | Gamache | Franklin, McAdie, Blake EMC: several | 2
Targeting strategies to improve hurricane track forecasts | Majumdar Aberson Toth | Franklin | 2

## Slide 24: FY03 Point of Contact Distribution Cyclogenesis and track forecasting projects
Proposal | PIs | TPC POC | Yrs
Objective and automated assessment of operational global forecast model predictions of tropical cyclone formation and life cycle | Harr | Pasch Avila Blake | 2
An updated baseline for track forecast skill through five days for the Atlantic and Northeastern and Northwestern Pacific basins | Aberson | Franklin Gross | 1
Quantifying tropical cyclone track forecast uncertainty and improving extended-range tropical cyclone track forecasts using an ensemble of dynamical models | Goerss | Beven Gross | 1
Transition of revised dynamical model track prediction evaluation expert system (DYMES) | Boothe | Stewart Roberts | 1

## Slide 25: FY03 Point of Contact Distribution Intensity and rainfall projects
Proposal | PIs | TPC POC | Yrs
Improving the validation and prediction of tropical cyclone rainfall | Pan Black Marchok | Stewart Molleda | 2
Implementation of the Advanced Objective Dvorak Technique (AODT) and Tropical Cyclone Intensity Estimation (TIE) algorithms at TPC | Kossin Velden | Beven, Rhome, Mainelli, Cobb, Brown | 2
Improvements in Deterministic and Probabilistic Tropical Cyclone Surface Wind Predictions | Knaff DeMaria | Lawrence Gross Sisko | 2
Development of a rapid intensification index for the eastern Pacific basin | Kaplan | Avila Sisko | 2
Developing an inner-core SST cooling predictor for use in SHIPS | Cione Gentemann Kaplan | Avila, Berg, Sisko, Blake | 2

## Slide 26: FY03 Individual Project Overviews Dynamical model upgrades, observations and assimilation

## Slide 27
Upgrades to the operational GFDL hurricane prediction system
Morris Bender (NOAA/GFDL)
Goals:
  Test GFS surface physics package
  Modify downdraft formulation in SAS scheme
  Improve momentum mixing in SAS scheme
  Include effect of evaporation in large-scale condensation
  Modify land-sea mask for consistency between atmospheric and ocean models
  Import and test latest version of Lin microphysics

## Slide 28
Improving the GFDL/URI coupled hurricane-ocean model for transition to operations
Isaac Ginis (Univ. of Rhode Island)
Goals:
  Improve ocean component of the coupled model in the Atlantic basin (include explicit init of Loop Current using altimeter data)
  Implement ocean coupling in eastern Pacific basin (reduce positive intensity forecast biases)
  Evaluate and transfer to operations a new high-resolution version of the coupled model (5 nm spacing inner mesh)
  Test and implement new air-sea flux parameterizations

## Slide 29
Hurricane model transitions to operations at NCEP/EMC
Hua-Lu Pan (EMC), Bob Tuleya (EMC contractor)
Goals:
  Test GFS shallow convection and surface parameterizations in GFDL model
  Test bulk microphysics packages
  Run parallel version with NOAH LSM in 2003 season
  Test WRF physics packages
  Test movable nest HWRF
  Evaluate Hurricane WRF prototype, compare to GFDL w/WRF physics packages, run the prototype operationally in 2005?

## Slide 30
Evaluation of upper ocean mixing parameterizations
Daniel Jacob (GEST/UMBC)
  Lynn Shay and George Halliwell (UM/RSMAS)
Goals
  Use primitive equation ocean model to simulate upper ocean response to three TCs (Gilbert, Isidore, Lili) using realistic forcing and several ocean vertical mixing models
  Compare simulated upper ocean thermal and current structure to data from AXBTs, conductivity, temperature and depth probes (AXCTDs), and current profilers (AXCPs)
  Identify mixing models that produce most realistic simulations; provide best vertical mixing parameterization to NCEP for use in coupled models

## Slide 31
Real-time dissemination of hurricane wind fields determined from airborne doppler
John Gamache (HRD)
Goals
  Implement existing Doppler radar wind analysis scheme onboard NOAA recon aircraft
  Transmit analysis from aircraft to TPC and into H*Wind
  Preliminary development and testing of superobs on the aircraft for eventual assimilation into models

## Slide 32
Targeting strategies to improve hurricane track forecasts
Sharanya Majumdar (Univ. of Miami/RSMAS)
  Sim Aberson (HRD), Zoltan Toth (EMC)
Goals
  Develop objective strategy: Ensemble Transform Kalman Filter (ETKF), used in winter storms, using operational ensemble forecasts
  Use present subjective targeting method operationally
  Identify cases in which ETKF selects targets similar to subjective method; re-run models to simulate ETKF being used operationally to produce sensitivity maps
  Refine ETKF software (incl. merge with flight track drawing under development) and procedures for transition to operations
  Operationally produce ETKF products that select best feasible flight tracks

## Slide 33: FY03 Individual Project Overviews FY03 Individual Project Overviews Tropical cyclogenesis, TC track forecasting algorithms

## Slide 34
Objective and automated assessment of operational global forecast model predictions of tropical cyclone formation and life cycle
Patrick Harr (Naval Postgraduate School)
Goals:
  Provide a tool for development of probabilistic measures of guidance accuracy among global model products related to TC formation and life cycle
  Discriminate between circulations in models that may develop as predicted and those that are false alarms
  Automatically and objectively identify and evaluate TC precursor circulations, and their physical characteristics, in global analysis and model forecast fields
  Summarize and catalogue model performance on a circulation for comparison with future circulations
  Provide web interface for operational assessment of models relevant to TC formation

## Slide 35
Analyzed and forecast quantities:
  850 mb relative vorticity
  Sea level pressure
  Shallow vertical wind shear (500-850 mb)
  Deep vertical wind shear (200-850 mb)
  1000-200 mb geopotential height thickness
  1000-500 mb temperature difference
  Vertical motion
  Total precipitation
  700-400 mb vapor pressure
  500-200 mb temperature difference between area within and outside of ellipse/circulation

## Slide 36
An updated baseline for track forecast skill through five days for the Atlantic and Northeastern and Northwestern Pacific basins
Sim Aberson (HRD)
Goals:
  Update CLIPER track models
  Incorporate recent best track data used to derive the models
  Improve calculation of current storm motion

## Slide 37
Quantifying tropical cyclone track forecast uncertainty and improving extended range forecasts using an ensemble of dynamical models
James Goerss (Naval Research Laboratory)
Goals
  Apply “CONU” approach to Atlantic and eastern Pacific basins to potentially include GFDN (FNMOC), COAMPS (FNMOC), and MM5 (AFWA) along with GUNA components
  Determine optimum mix of models at different lead times
  Perform statistical evaluations of consensus forecast errors, stratified by initial quantities known at time of forecast (e.g., spread, number of models available to consensus, and TC initial intensity, forward motion, and location)
  Operationally provide tabular and graphical displays of uncertainty in each consensus forecast
  Validate uncertainty graphic using cross-validation techniques on 2000-02/3 database on a storm-by-storm basis
  Provide statistical evaluation software to be used to update uncertainty database at the end of each season, to incorporate changes to individual models

## Slide 38
Transition of revised dynamical model track prediction evaluation expert system
Mark Boothe (Naval Postgraduate School)
Goals
  Create revised DYMES that implements the Atlantic error mechanisms determined with previous funding
  Demonstrate operational utility during real-time tests

## Slide 39: FY03 Individual Project Overviews TC Intensity

## Slide 40
Implementation of the Advanced Objective Dvorak Technique (AODT) and the Tropical Cyclone Intensity Estimation (TIE) model algorithms
James Kossin (CIMSS/Univ. of Wisconsin)
Chris Velden (CIMSS/Univ. of Wisconsin)
Goals:
  Implement latest version of AODT in NAWIPS, applicable to all stages of TC, non-McIDAS, can be automated
  Implement rudimentary version of TIE model in NAWIPS: fully objective regression between recon pressure and IR predictors, SST, and latitude of the TC; additional predictors to be added (e.g., synoptic environment, microwave imagery)
  Integrate AODT and TIE into single code package

## Slide 41
Improvements in deterministic and probabilistic tropical cyclone surface wind predictions
John Knaff (CIRA/CSU) With Mark DeMaria (NESDIS/ORA)
Goals:
  Develop and evaluate new component to SHIPS model utilizing recon and GOES IR data to better determine inner core structure
  Test neural network prediction method in SHIPS to account for nonlinear interactions between predictors
  Provide fields of the probability of surface wind speeds exceeding specified thresholds over certain time intervals

## Slide 42: Michelle 11/02/01 00 UTC Intensity Forecast (hr: kt): 0: 55, 24: 75, 48: 90, 72: 95 , 96: 70, 120: 60
0-24 hr 24-48 hr 48-72 hr
CI=5% CI=2%
72-96 hr 96-120 hr 0-120 hr
CI=10%
CI=10% CI=10% CI=5%
Experimental Probability of 64 kt Winds

## Slide 43
Development of a rapid intensification index for the eastern Pacific basin
John Kaplan (HRD) With Mark DeMaria (NOAA/NESDIS/ORA)
Goals
  Develop RI index for the eastern Pacific using methodology similar to that for existing Atlantic index
    Use 1989-2003 SHIPS database
    95th percentile of 24 h over-water intensity changes
    Thresholds of significant predictors of RI will be mean values from all RI cases
  Output RI probability estimate with each operational eastern Pacific SHIPS forecast
  Modify existing code and provide training so that it can be used by TPC to re-derive the eastern Pacific index for future seasons

## Slide 44
Developing an inner-core SST cooling predictor for use in SHIPS
Joe Cione (HRD)
Chelle Gentemann (Remote Sensing Systems) and John Kaplan (HRD)
Goals
  Test algorithm for use in SHIPS that relates the estimated amount of SST cooling directly under the storm to subsequent TC intensity change
  Extend algorithm, based on a developmental 23-hurricane sample (1975-2002) of observations (AXBTs, buoys), to weaker systems (by 2005)
  To run operationally, predict (rather than observe) inner-core SST cooling using regression with ambient SST and storm location/speed/intensity
  Improve upon weekly Reynolds SSTs that provide initialization; higher spatial and temporal resolution
  Test additional predictors related to subsurface upper ocean parameters

## Slide 45: FY03 Individual Project Overviews TC Rainfall

## Slide 46
Improving the validation and prediction of tropical cyclone rainfall
Hua-Lu Pan (EMC), Robert Black (HRD), Tim Marchok (GFDL)
Goals:
  Develop new rainfall validation schemes that provide a baseline of comparison for different forecast systems
  Provide new forecasting tool, based on the benchmark R-CLIPER, that incorporates information related to vertical shear and storm track, and can be run operationally
  Generate error statistics for rainfall forecasts using traditional and new validation techniques for the operational GFDL, Eta, and GFS models, and the R-CLIPER and modified R-CLIPER.

## Slide 47: 2003-04 JHT Project Schedule
Semi-annual reports due 31 January 2004
Each PI make presentation at IHC in March 2004, possibly meet with TPC/NHC points of contact
Make preparations for and begin real-time testing and evaluation during 2004 hurricane season
Renewal proposals from PIs due 15 May 2004
Second year of funded activity for renewed projects begins July/Aug 2004