## Slide 1: Joint Hurricane Testbed (JHT) 2006 IHC Update
USWRP
Dr. Jiann-Gwo Jiing JHT Director TPC/NHC 22 March 2006

## Slide 2: Outline
Status of Second Round Projects (FY03-04)
Status of Third Round Projects (FY05-06)
Major JHT Activities in 2006

## Slide 3
Background information
  15 projects were initially funded late in FY03: 3 one-year and 12 two-year projects
  Three one-year projects concluded (Aug 2004)
    Decisions on operational implementation by TPC Director in December 2004
    Two projects accepted for operational implementation and were implemented before 2005 Hurricane Season started
2005-present activities
  12 two-year projects completed in August 2005
  Final stage of evaluation
  Decisions on operational implementation for 8 projects in late March 2006 by TPC Director
  Decisions on operational implementation for 4 model related projects in April 2006 by EMC Director
Status of 15 Second Round Projects (FY03-04 Funding)

## Slide 4
Background information:
  Announcement of Opportunity (30 June 2004)
  Review of proposals completed and recommendations made in late January 2005
  Total available funding: ~$1.2 Million
PIs from federal labs received funding in late March (OAR) and June (DOD) 2005
Non-federal PIs received funding between late June and August 2005
JHT and project point of contacts coordinated with PIs to develop timelines
Testing and evaluation during 2005 hurricane season
Status of 15 Third Round Projects (FY05-06 Funding)

## Slide 5
Primary Area of Focus | # of Projects
Improvements to dynamical models (for track, intensity, and precipitation forecasts) | 4
Intensity forecast guidance | 4
Enhancements to observed data, assimilation | 3
Tropical cyclone structure/wind distribution | 2
Track forecast guidance | 1
Enhancements to operational environment | 1
Total | 15
Third Round Project Focus Areas

## Slide 6
3rd Round (FY05) Funding Distribution Total $1.2M
NOAA 39%
Private Companies 9%
State and Private Universities 36%
Navy (NPS, NRL) 16%

## Slide 7: Implementation
First round:
  10 projects, one was not continued after first year
  Two projects continued into 2nd round
  Out of the seven accepted, 6.5 were implemented
Second round:
  Three one-year projects, 2 implemented, one not accepted
  12 two-year projects being evaluated (some already implemented)

## Slide 8: Implementation
Some relative easy
Some very complicated
Some implemented by the PIs/other Centers
Some implemented by TPC staff/PIs
Some implemented by JHT staff/PIs

## Slide 9
Tropical Cyclone Rainfall Climatology and Persistence
(R-CLIPER) Model
Example real-time output in NAWIPS during Hurricane Lili (2002)

## Slide 10: GFDL

## Slide 11
AMSU Intensity/Size Estimation

## Slide 12
Experimental Cumulative Wind Speed Probabilities
This product will be operational in 2006
Computed each forecast cycle for all active tropical cyclones in the Atlantic, eastern/central Pacific, and western Pacific basins
Computed on 2-D grids with 0.5-degree lat/lon spacing
Provides probabilities of the surface wind speed equal to or exceeding 34, 50, and 64 kt over specified time intervals (0-120 hours in 12-hour intervals)
  Individual interval or cumulative probabilities
Gridded, graphical, and text products can be produced

## Slide 13: Major Activities for 2006
Present final reports on eight 2nd round non-EMC related projects to TPC Director (mid-March)
Rounds 3 PI presentations at the 60th IHC in Mobile, AL (March 20-24)
Decisions for implementation of eight 2nd round projects by TPC Director (March 31)
Decisions on implementation of four 2nd round model-related projects by EMC (April)
Second year funding proposals for 3rd round projects due for SC review (April and July 2006)
  Requested $1.265M, $1.15M available
Real time testing and evaluation

## Slide 14: Major Activities for 2006 (Preparing for the next round of funding)
Revise Announcement of Opportunity (AO) for round 4 (FY07-08) projects. Send to DOC legal counsel for review in early April
Round 4 AO released (June 30)
Pre-application for round 4 proposals due July 31
Full proposals due October 30
Receive final scores from the SC (January 8, 2007)
TPC and JHT Directors’ decision on which proposals to recommend for funding (January 29, 2007)

## Slide 15: Changes
Russ Elsberry retired from the JHT Steering Committee (SC)
Jeff Hawkins (NRL) elected to the SC
Frank Marks retired from the SC
Chris Landsea retired from the JHT adm. Assist. position (HRD)
Shirly Murillo replaces Chris Landsea as the JHT adm. Assist. (HRD)
Chris Landsea elected to the JHT SC (HRD)
Rich Knabb retired from the JHT adm. assist. position (TPC)
Chris Landsea joined the TPC and became the JHT adm. Assist. (TPC)
John Gamache elected to the SC (HRD)

## Slide 16
www.nhc.noaa.gov/jht/index.shtml
JHT Website

## Slide 17
Acknowledgements
  JHT Steering Committee
  JHT administrative assistants
  Alison Krautkramer, JHT meteorologist/programmer
  JHT principal investigators and other funded participants
  Ward Seguin and John Gaynor (OAR)
  TPC/NHC management and admin staff
  TPC and EMC forecaster and technical points of contact
  TPC/TSB IT staff

## Slide 18: Thank you

## Slide 19
Supplemental Slides

## Slide 20: Input for JHT Project Reports to the TPC Director
Project PI final report
JHT staff members’ assessments
TPC Point of Contact (POC) feedback
JHT IT Facilitator report
  IT transfer status
  Compatibility and support issues
  Estimates of costs to implement and support
  Input from TPC Technical Support Branch Chief

## Slide 21: FY05 JHT Proposal Review Criteria (Condensed)
Relevance to program goals (40 pts)
  Research maturity (10 pts)
  Priority-to-payoff factors (25 pts)
  Other agency use (5 pts)
Technical merit (40 pts)
  Risk-to-payoff factors (10 pts)
  Testing (10 pts)
  Operational usage (10 pts)
  Technical compatibility (10 pts)
Overall qualification of applicants (10 pts)
Project costs (10 pts)

## Slide 22
FY05 Review Process
Preapplications (Letters of Intent) reviewed in Aug 2004
  40 preapplications reviewed
  18 recommended to submit a full proposal
Full proposals reviewed during Nov 2004 – Jan 2005
  19 proposals reviewed
  Proposals independently reviewed and scored by 7 JHT Steering Committee members based upon review criteria listed in the AFFO

## Slide 23
Primary Areas of Focus | # of Projects
Improvements to dynamical models (for track, intensity, and precipitation forecasts) | 4
Track forecast guidance algorithms | 3
Intensity forecasting algorithms | 3
Enhancements to observed data, assimilation | 2
Initial intensity estimation | 1
Tropical cyclogenesis | 1
Rainfall | 1
Total | 15
JHT Second Round (FY03-04) Project Focus Areas

## Slide 24: Second Round (FY03-04) Projects Dynamical model upgrades, obs/assimilation projects
Proposal | PIs | TPC POC | Yrs
Upgrades to the operational GFDL hurricane prediction system | Bender (GFDL) | Pasch Rhome | 2
Improving the GFDL/URI coupled hurricane-ocean model | Ginis (U. RI) | Pasch Rhome | 2
Hurricane model transitions to operations at NCEP/EMC | Pan (NCEP) | Pasch Rhome | 2
Evaluation of upper ocean mixing parameterizations | Jacob (U. MD) Shay (U. M) Halliwell (U. M) | Lawrence Mainelli | 2
Real-time dissemination of hurricane wind fields determined from airborne doppler | Gamache (HRD) | Franklin, McAdie, Blake EMC: several | 2
Targeting strategies to improve hurricane track forecasts | Majumdar(UM) Aberson (HRD) Toth (NCEP) | Franklin | 2

## Slide 25: Second Round (FY03-04) Projects Cyclogenesis and track forecasting projects
Proposal | PIs | TPC POC | Yrs
Objective and automated assessment of operational global forecast model predictions of tropical cyclone formation and life cycle | Harr (NPS) | Pasch Avila Blake | 2
An updated baseline for track forecast skill through five days for the Atlantic and Northeastern and Northwestern Pacific basins | Aberson (HRD) | Franklin Gross | 1 Accepted and implemented
Quantifying tropical cyclone track forecast uncertainty and improving extended-range tropical cyclone track forecasts using an ensemble of dynamical models | Goerss (NRL) | Beven Gross | 1 Accepted and implemented
Transition of revised dynamical model track prediction evaluation expert system (DYMES) | Boothe (NPS) | Stewart Roberts | 1 Not accepted

## Slide 26: Second Round (FY03-04) Projects Intensity and rainfall projects
Proposal | PIs | TPC POC | Yrs
Improving the validation and prediction of tropical cyclone rainfall | Pan (NCEP) Black (HRD) Marchok (NCEP) | Stewart Molleda | 2
Implementation of the Advanced Objective Dvorak Technique (AODT) and Tropical Cyclone Intensity Estimation (TIE) algorithms at TPC | Kossin (U. WI) Velden (U. WI) | Beven, Rhome, Mainelli, Cobb, Brown | 2
Improvements in Deterministic and Probabilistic Tropical Cyclone Surface Wind Predictions | Knaff (U. Co) DeMaria (NESDIS) | Lawrence Gross Sisko | 2
Development of a rapid intensification index for the eastern Pacific basin | Kaplan (HRD) | Avila Sisko | 2
Developing an inner-core SST cooling predictor for use in SHIPS | Cione (HRD) Gentemann Kaplan (HRD) | Avila, Berg, Sisko, Blake | 2

## Slide 27: JHT Third Round Projects Dynamical model upgrades, observational, and assimilation projects
Proposal Title | PIs | TPC POC
Hurricane Model Transition to Operations at GFDL/NOAA | Bender | Pasch, Rhome
Hurricane Model Transition to Operations at GFDL/NOAA | Tuleya | Pasch
Drag Coefficient and Wind Speed Dependence in TCs | Powell | Franklin
Dynamic Initialization to Improve TC Intensity and Structure Forecasts | Liou | Pasch
Operational SFMR-NAWIPS Airborne Processing and Data Distribution Products | Carswell, Black, Chang | Beven, Mainelli, Sisko, Lauer
Mapping of Topographic Effects on Maximum Sustained Surface Wind Speeds in Landfalling Hurricanes | Miller | Beven
Assimilating Moisture Information from GPS Dropwindsondes into the NOAA Global Forecast System | Aberson | Franklin, Blake
WSR-88D-derived Diagnosis of Tropical Cyclone Intensity Changes Near Landfall | Lee, Harasti | Stewart, McAdie
Fed
Fed
Fed
Fed

## Slide 28: JHT Third Round Projects Intensity, structure, and track projects
Proposal Title | PIs | TPC POC
Improved Statistical Intensity Forecast Models | Knaff, DeMaria, Kaplan | Avila, Sisko
Enhancement of SHIPS Using Passive Microwave Imager Data | Cecil | Stewart, Sisko
Eastern Pacific Ocean Heat Content Estimates for SHIPS Forecasts | Shay, DeMaria | Avila, Mainelli
Continued Development of Tropical Cyclone Wind Probability Products | Knaff, DeMaria | “Lawrence”, Gross
Estimating Tropical Cyclone Wind Radii Utilizing an Empirical Inland Wind Decay Model | Kaplan | Stewart, Gross
Prediction of Consensus TC Track Forecast Error and Correctors to Improve Consensus TC Track Forecasts | Goerss | Beven, Gross
Development and Implementation of NHC/JHT Products in ATCF | Sampson | “Lawrence”, Sisko, Gross
Fed
Fed
Fed