## Slide 1: Joint Hurricane Testbed (JHT) 2008 IHC Update
USWRP
Jiann-Gwo Jiing JHT Director NHC
Shirley Murillo
NOAA/HRD
Chris Landsea
NHC
5 March 2008

## Slide 2: Outline
Status of Third Round Projects (FY05-06)
Status of Fourth Round Projects (FY07-08)
Challenges for 2008

## Slide 3
Status of 3rd round JHT projects (FY05-07)
NOAA projects completed in April 2007
Non-NOAA projects completed in August 2007
TPC/NHC POC provided evaluation and feedback
JHT staff conducts IT evaluation
JHT staff prepares final evaluations and reports to TPC Director

## Slide 4: Status of 3rd round JHT projects (FY05-07)
Center Directors’ decision on project acceptance
  15 projects completed (August 2007)
  11.5 projects accepted for operational implementation
  3.5 projects require further evaluation
Status of implementation
  10 accepted projects implemented

## Slide 5: JHT Third Round (FY05-06) Projects Dynamical model upgrades, observational, and assimilation projects
Proposal Title | PIs | NHC POC | S
Hurricane Model Transition to Operations at GFDL/NOAA | Bender | Pasch, Rhome | I
Hurricane Model Transition to Operations at GFDL/NOAA | Tuleya | Pasch | I
Drag Coefficient and Wind Speed Dependence in TCs | Powell | Franklin | I
Dynamic Initialization to Improve TC Intensity and Structure Forecasts | Liou | Pasch | P
Operational SFMR-NAWIPS Airborne Processing and Data Distribution Products | Carswell, Black, Chang | Beven, Mainelli, Sisko, Lauer | P/I
Mapping of Topographic Effects on Maximum Sustained Surface Wind Speeds in Landfalling Hurricanes | Miller | Beven | I
Assimilating Moisture Information from GPS Dropwindsondes into the NOAA Global Forecast System | Aberson | Franklin, Blake | I
WSR-88D-derived Diagnosis of Tropical Cyclone Intensity Changes Near Landfall | Lee, Harasti | Stewart, McAdie | I

## Slide 6: JHT Third Round (FY05-06) Projects Intensity, structure, and track projects
Proposal Title | PIs | NHC POC | S
Improved Statistical Intensity Forecast Models | Knaff, DeMaria, Kaplan | Avila, Sisko | I
Enhancement of SHIPS Using Passive Microwave Imager Data | Cecil | Stewart, Sisko | P
Eastern Pacific Ocean Heat Content Estimates for SHIPS Forecasts | Shay, DeMaria | Avila, Mainelli | P
Continued Development of Tropical Cyclone Wind Probability Products | Knaff, DeMaria | Lauer | I
Estimating Tropical Cyclone Wind Radii Utilizing an Empirical Inland Wind Decay Model | Kaplan | Stewart, | I
Prediction of Consensus TC Track Forecast Error and Correctors to Improve Consensus TC Track Forecasts | Goerss | Beven | I
Development and Implementation of NHC/JHT Products in ATCF | Sampson | Sisko | I

## Slide 7: Highlights of Implemented 3rd Round Projects

## Slide 8
Topographic Speed-up Mapping Tool

## Slide 9: Status of 4th round (2007-2009) projects
Application (28) Review completed in January 2007
JHT & TPC Director sent recommendations (10 projects) to NOAA in early March 2007
USWRP sent notifications to PIs on March 16
Funding for NOAA PIs transferred in June 2007
Funding for Navy and private PIs transferred in late September

## Slide 10
4th Round (FY07) Recommended Funding Distribution Total $1.04M ($1.5M announced)
Private Companies 24%
NOAA 20%
State and Private Universities 33%
Navy (NPS, NRL) 11%
NASA 12%

## Slide 11
Primary Area of Focus | # of Projects
Improvements to dynamical models (for track, intensity, and precipitation forecasts) | 5
Statistical intensity forecast guidance | 1
Enhancements to observed data, assimilation | 0
Tropical cyclone structure/wind/wave distribution | 2
Track forecast guidance | 1
Enhancements to operational environment | 1
Total | 10*
4th Round Recommended Project Focus Areas

## Slide 12: Challenges for FY08
Managing 10 projects with wide spread starting dates
Review 4th round two-year projects for second year funding
Preparation of the Announcement of Opportunity for the 5th round (FY09-10)
Real-time Testing and evaluation
Implementation of new projects (NHC)
Future funding (FY09 - )

## Slide 13: Summary of JHT Activities 2001-2007
Total projects funded (round 1-4) – 50
Number of projects completed (round 1-3) – 39
(One was denied funding after first year)
Number of projects accepted for implementation – 28.5
Number of completed projects not accepted – 4
Number of completed projects pending further evaluation – 6.5
Number of projects implemented – 25
Dedicated NHC & JHT staff, and close collaborations between the PIs,
NHC forecasters and support staff

## Slide 14
Acknowledgements
  JHT Steering Committee
  Shirley Murillo, NOAA/HRD, JHT Admin. Asst.
  Chris Landsea, NHC, JHT Admin. Asst.
  Jose Salazar, JHT meteorologist/programmer
  JHT principal investigators and other funded participants
  USWRP
  NHC and EMC forecaster and points of contact
  NHC/Technical Support Branch staff
  NHC admin staff

## Slide 15
JHT Website
Go to www.nhc.noaa.gov

## Slide 16: Questions?

## Slide 17
Supplemental Slides

## Slide 18: JHT Infrastructure
Personnel
Quarter-time Director (NOAA FTE)
7-member Steering Committee
  Three from NOAA (one TPC), two from DOD, and two from the academic community
  TPC member serves as co-Chair
Two quarter-time administrative assistants (NOAA FTE)
One IT Facilitator
Computing Resources
Server and workstations
Software

## Slide 19: Factors Considered in TPC Decisions on Operational Implementation
Forecast or Analysis Benefit: expected improvement in operational forecast and/or analysis accuracy
Efficiency: adherence to forecaster time constraints and ease of use needs
Compatibility: IT compatibility with operational hardware, software, data, communications, etc.
Sustainability: availability of resources to operate, upgrade, and/or provide support

## Slide 20: JHT Fourth Round (FY07-08) Projects Intensity, structure, and track projects
Proposal Title | PI | TPC POC
Improving the Hurricane WRF-Ocean Coupled System for Transition to Operations | Ginis, Isaac (Univ. of Rhode Island) | Pasch, Mainelli, Cangialosi Lozano/Tolman (EMC)
An Improved Wind Probability Estimation Program | Stan Kidder (CSU), DeMaria, Mark (NESDIS) Harr, Pat (NPS) | Knabb, Lauer, Mainelli
Hurricane Model Transitions to Operations at NCEP/EMC | Tuleya, Bob (SAIC) | Pasch, Fiorino, Rhome, Surgi (EMC)
Web-ATCF, user Requirements and Intensity Consensus | Sampson, Charles (NRL) | Knabb, Franklin, Sisko
Evaluation and Improvement of Ocean Model Parameterizations for NCEP Operations | Shay, Nick (UM) | Avila, Rhome, Baig, Lozano(EMC)

## Slide 21: JHT Fourth Round (FY07-08) Projects Intensity, structure, and track projects
Proposal Title | PI | TPC POC
Operational Use of Near-Real Time Surface Directional Wave Spectra Generated from NOAA Scanning Radar Altimeter Range Measurements | Walsh, Edward (NASA/GFSC) | Beven, Willis, Brown, Baig
High Wind Drag Coefficient and Sea Surface Roughness in Shallow Water | Powell, Mark (NOAA/AOML) | Franklin, Blake, Tolman (EMC)
Validation and Processing Tools for the AF Reserves Command 53rd Weather Reconnaissance Squadron WC-130J Multi-Aircraft SFMR Systems | J. Carswell (RSS, Inc.) P. Black (AOML) | Beven, Brown, Sisko, Christensen
Evaluation and Improvement of Spray-Modified Air-Sea Enthalpy and Momentum Flux Paramete-rizations for operational Hurricane Prediction | J. Bao, C. Fairall, J. Wilczak (ESRL) | Pasch, Berg, Fiorino, Surgi/Kwon (EMC)
TC Dressing: A Probabilistic Approach to Providing State Dependent, Non-Isotropic Forecast Track Error Guidance | J. Hansen J. Goerss (NRL) | Franklin, Blake, Sisko, Mundell